## Tracker
MedVoice v3.4 — 6-Week Delivery Tracker
Andalusia Group ¦ AI Team ¦ Update only the yellow cells. Task rows, flags, team progress and the Gantt update automatically.
Project start |  | 2026-10-04 |  |  |  |  | Team | Hours | Planned % | Done % | Blocked | Late | To check
Meeting date |  | 2026-10-04 |  |  |  |  | Ahmed Hamdy | 86 | 0% | 13.26% | 0 | 0 | 7
Working day |  | 1 |  |  |  |  | Doha | 89 | 0% | 23.4% | 0 | 0 | 0
Baseline go-live |  | 2026-11-12 |  |  |  |  | Mohamed Essam | 102 | 0% | 0% | 0 | 0 | 5
Forecast go-live |  | 2026-11-08 |  |  |  |  | External teams | — | 0% | 15.48% | 0 | 0 | 1
Ahead (+) / behind (−) |  | 4 |  |  |  |  | Whole project | 277 | 0% | 13.63% | 0 | 0 | 0
Planned % = where the plan expects us on the meeting date. "To check" = status and % do not match (e.g. In progress at 0%).
[14 empty] | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01 | 2026-11-08
ID | Task / subtask | Owner | Hours | Days | Start | End | Depends on | Done when | Status | % done | Checklist | Flag | Notes / blockers | W1 | W2 | W3 | W4 | W5 | W6 | SD | ED | DAYS | LVL | TEAM | PREV | P0
PRE-REQUISITES — outside the AI team
X1 | Approve use of de-identified logged sessions as the gold set | Compliance | 1 | 5 | 2026-10-04 | 2026-10-08 | — | Signed approval received | In progress | 50% | 0% |  | Essam calls Germeen | 1 | [5 empty] | 1 | 5 | 5 | T | Ext
X2 | Export ICD-10 code master from the HIS coding system | Coding team | 1 | 3 | 2026-10-04 | 2026-10-06 | — | File delivered and readable | In progress | 50% | 0% |  | Essam calls Germeen | 1 | [5 empty] | 1 | 3 | 3 | T | Ext
X3 | Confirm residency: Foundry region; continued use of Munsit and Voxtral APIs | Compliance | 1 | 5 | 2026-10-04 | 2026-10-08 | — | Written approval | In progress | 50% | 0% |  | Essam calls Germeen | 1 | [5 empty] | 1 | 5 | 5 | T | Ext
X4 | Sign acceptance thresholds and pilot site | Steering | 1 | 2 | 2026-10-04 | 2026-10-05 | — | Signed gate sheet | In progress | 0% | 0% | Check | Asked Doha to prepare | 1 | [5 empty] | 1 | 2 | 2 | T | Ext
AHMED HAMDY — Platform & performance
A1 | Fix LLM concurrency: shared async client, 45 s timeout, backoff + jitter, per-model limits, async streaming | Ahmed Hamdy | 9 | 2 | 2026-10-04 | 2026-10-05 | — | 30 parallel analyses complete; no event-loop blocking; ≤ 3 retries each | In progress | 99.44% | 0% |  |  | 1 | [5 empty] | 1 | 2 | 2 | T | Ahmed Hamdy
A1.1 | Shared async client + 45 s timeout, no hidden retries | Ahmed Hamdy | 3 | 1 | 2026-10-04 | 2026-10-04 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 1 | 1 | 1 | S | Ahmed Hamdy
A1.2 | Async streaming for refine / translate | Ahmed Hamdy | 1 | 1 | 2026-10-04 | 2026-10-04 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 1 | 1 | 1 | S | Ahmed Hamdy
A1.3 | Backoff + jitter on 429/5xx; remove key rotation | Ahmed Hamdy | 1 | 1 | 2026-10-04 | 2026-10-04 |  |  | In progress | 95% | 0% |  |  | 2 | [5 empty] | 1 | 1 | 1 | S | Ahmed Hamdy
A1.4 | Per-model concurrency limits (semaphores) | Ahmed Hamdy | 1 | 1 | 2026-10-04 | 2026-10-04 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 1 | 1 | 1 | S | Ahmed Hamdy
A1.5 | Test: 30 parallel analyses | Ahmed Hamdy | 3 | 2 | 2026-10-04 | 2026-10-05 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 1 | 2 | 2 | S | Ahmed Hamdy
A2 | Azure foundation: Key Vault, managed identities, private endpoints, App Insights | Ahmed Hamdy | 4 | 1 | 2026-10-06 | 2026-10-06 | — | No secrets in code; private access only; traces visible | In progress | 0% | 0% |  |  | 1 | [5 empty] | 3 | 3 | 1 | T | Ahmed Hamdy | A1
A2.1 | Key Vault; move all secrets | Ahmed Hamdy | 1 | 1 | 2026-10-06 | 2026-10-06 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 3 | 3 | 1 | S | Ahmed Hamdy
A2.2 | Managed identities + RBAC | Ahmed Hamdy | 1 | 1 | 2026-10-06 | 2026-10-06 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 3 | 3 | 1 | S | Ahmed Hamdy
A2.3 | Private endpoints + DNS (Foundry, Key Vault) | Ahmed Hamdy | 1 | 1 | 2026-10-06 | 2026-10-06 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 3 | 3 | 1 | S | Ahmed Hamdy
A2.4 | App Insights, no patient text in logs | Ahmed Hamdy | 1 | 1 | 2026-10-06 | 2026-10-06 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 3 | 3 | 1 | S | Ahmed Hamdy
B5 | Incremental structuring: structure each transcript segment live, consolidate at end | Ahmed Hamdy | 8 | 1 | 2026-10-07 | 2026-10-07 | B1 | Final note ≤ 3 s after stop; no fidelity loss | In progress | 0% | 0% |  |  | 1 | [5 empty] | 4 | 4 | 1 | T | Ahmed Hamdy | A2 | B1
B5.1 | Structure each final transcript segment with running context | Ahmed Hamdy | 4 | 1 | 2026-10-07 | 2026-10-07 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 4 | 4 | 1 | S | Ahmed Hamdy
B5.2 | Consolidation pass when dictation stops | Ahmed Hamdy | 2 | 1 | 2026-10-07 | 2026-10-07 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 4 | 4 | 1 | S | Ahmed Hamdy
B5.3 | Compare with one-shot on 10 transcripts | Ahmed Hamdy | 2 | 1 | 2026-10-07 | 2026-10-07 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 4 | 4 | 1 | S | Ahmed Hamdy
B4 | Reasoning router: rule-based triggers, GPT-5.6 Terra default, one-step escalation to Sol, audit | Ahmed Hamdy | 10 | 2 | 2026-10-11 | 2026-10-12 | B3, B0 | Every routed case has an audit entry; tests pass | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 6 | 7 | 2 | T | Ahmed Hamdy | B5 | B3 | B0
B4.1 | Trigger rules as a pure function | Ahmed Hamdy | 4 | 1 | 2026-10-11 | 2026-10-11 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 6 | 6 | 1 | S | Ahmed Hamdy
B4.2 | Terra default; one escalation to Sol | Ahmed Hamdy | 2 | 1 | 2026-10-11 | 2026-10-11 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 6 | 6 | 1 | S | Ahmed Hamdy
B4.3 | Audit record + unit tests | Ahmed Hamdy | 4 | 2 | 2026-10-11 | 2026-10-12 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 6 | 7 | 2 | S | Ahmed Hamdy
A4 | CI/CD pipeline and staging environment | Ahmed Hamdy | 11 | 2 | 2026-10-13 | 2026-10-14 | A2 | Pipeline green; staging reachable privately | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 8 | 9 | 2 | T | Ahmed Hamdy | B4 | A2
A4.1 | CI pipeline: lint, test, build, push | Ahmed Hamdy | 3 | 1 | 2026-10-13 | 2026-10-13 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 8 | 8 | 1 | S | Ahmed Hamdy
A4.2 | Staging environment | Ahmed Hamdy | 4 | 1 | 2026-10-13 | 2026-10-13 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 8 | 8 | 1 | S | Ahmed Hamdy
A4.3 | Smoke test + approval gate to production | Ahmed Hamdy | 4 | 2 | 2026-10-13 | 2026-10-14 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 8 | 9 | 2 | S | Ahmed Hamdy
A3 | Deploy Foundry models: GPT-4o mini, GPT-5.6 Luna / Terra / Sol, structuring LLM | Ahmed Hamdy | 7 | 1 | 2026-10-15 | 2026-10-15 | A2 | All endpoints reachable via private endpoint; valid JSON | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 10 | 10 | 1 | T | Ahmed Hamdy | A4 | A2
A3.1 | Deploy GPT-4o mini, Luna, Terra, Sol, DeepSeek V3 | Ahmed Hamdy | 1 | 1 | 2026-10-15 | 2026-10-15 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 10 | 10 | 1 | S | Ahmed Hamdy
A3.2 | Record quotas; add to config | Ahmed Hamdy | 2 | 1 | 2026-10-15 | 2026-10-15 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 10 | 10 | 1 | S | Ahmed Hamdy
A3.3 | Strict-JSON smoke test; content-filter check | Ahmed Hamdy | 4 | 1 | 2026-10-15 | 2026-10-15 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 10 | 10 | 1 | S | Ahmed Hamdy
A5 | Load-test harness for WebSocket + SSE sessions | Ahmed Hamdy | 10 | 2 | 2026-10-18 | 2026-10-19 | A4 | Harness runs both languages | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 11 | 12 | 2 | T | Ahmed Hamdy | A3 | A4
A5.1 | Locust session script (audio stream + SSE) | Ahmed Hamdy | 6 | 1 | 2026-10-18 | 2026-10-18 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 11 | 11 | 1 | S | Ahmed Hamdy
A5.2 | Export timings per session | Ahmed Hamdy | 4 | 2 | 2026-10-18 | 2026-10-19 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 11 | 12 | 2 | S | Ahmed Hamdy
A7 | Resilience: health checks, circuit breakers, model fallback, admission control | Ahmed Hamdy | 15 | 2 | 2026-10-20 | 2026-10-21 | M4 | Fallbacks exercised in tests | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 13 | 14 | 2 | T | Ahmed Hamdy | A5 | M4
A7.1 | Health and readiness probes | Ahmed Hamdy | 4 | 1 | 2026-10-20 | 2026-10-20 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 13 | 13 | 1 | S | Ahmed Hamdy
A7.2 | Circuit breaker per provider | Ahmed Hamdy | 6 | 2 | 2026-10-20 | 2026-10-21 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 13 | 14 | 2 | S | Ahmed Hamdy
A7.3 | Model fallbacks (4o mini ↔ Luna, Terra → Sol) | Ahmed Hamdy | 2 | 1 | 2026-10-21 | 2026-10-21 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 14 | 14 | 1 | S | Ahmed Hamdy
A7.4 | Admission control (503 + Retry-After) | Ahmed Hamdy | 3 | 1 | 2026-10-21 | 2026-10-21 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 14 | 14 | 1 | S | Ahmed Hamdy
A6 | Load test 1→50 sessions; tune limits; confirm p95 latency and 429 rate | Ahmed Hamdy | 12 | 2 | 2026-10-22 | 2026-10-25 | A5, A7, M4 | p95 ≤ target; 429 < 1%; accuracy loss < 2 pts | Not started | 0% | 0% |  |  |  |  | 1 | 1 |  |  | 15 | 16 | 2 | T | Ahmed Hamdy | A7 | A5 | A7 | M4
A6.1 | Ramp 1 → 50 sessions per language | Ahmed Hamdy | 5 | 1 | 2026-10-22 | 2026-10-22 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 15 | 15 | 1 | S | Ahmed Hamdy
A6.2 | Accuracy check at peak (20 encounters) | Ahmed Hamdy | 3 | 1 | 2026-10-22 | 2026-10-22 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 15 | 15 | 1 | S | Ahmed Hamdy
A6.3 | Tune limits; capacity report | Ahmed Hamdy | 4 | 1 | 2026-10-25 | 2026-10-25 |  |  | Not started | 0% | 0% | [5 empty] | 2 |  |  | 16 | 16 | 1 | S | Ahmed Hamdy
DOHA — Clinical AI
B1 | Structuring prompt + schema: sections, translation, speaker labels with confidence, no-inference rules, routing signals | Doha | 14 | 2 | 2026-10-04 | 2026-10-05 | — | All 20 tests pass; Clinical Lead approves schema | In progress | 77.14% | 0% |  |  | 1 | [5 empty] | 1 | 2 | 2 | T | Doha
B1.1 | Structured-note JSON schema | Doha | 4 | 1 | 2026-10-04 | 2026-10-04 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 1 | 1 | 1 | S | Doha
B1.2 | Prompt: no-inference + translation rules | Doha | 4 | 1 | 2026-10-04 | 2026-10-04 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 1 | 1 | 1 | S | Doha
B1.3 | Arabic / mixed few-shot examples | Doha | 2 | 1 | 2026-10-05 | 2026-10-05 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 2 | 2 | 1 | S | Doha
B1.4 | 20 fidelity tests | Doha | 4 | 1 | 2026-10-05 | 2026-10-05 |  |  | In progress | 20% | 0% |  |  | 2 | [5 empty] | 2 | 2 | 1 | S | Doha
B0 | Keep term correction before structuring; add red-flag lexicon for routing | Doha | 4 | 1 | 2026-10-06 | 2026-10-06 | B1 | Lexicon file committed; red flags detected in tests | In progress | 40% | 0% |  |  | 1 | [5 empty] | 3 | 3 | 1 | T | Doha | B1 | B1
B0.1 | Keep term correction before structuring | Doha | 1 | 1 | 2026-10-06 | 2026-10-06 |  |  | Done | 100% | 0% | Done |  | 2 | [5 empty] | 3 | 3 | 1 | S | Doha
B0.2 | Red-flag lexicon file + routing signal | Doha | 3 | 1 | 2026-10-06 | 2026-10-06 |  |  | In progress | 20% | 0% |  |  | 2 | [5 empty] | 3 | 3 | 1 | S | Doha
B3 | Reasoning prompt: ICD-10 (edition stated), diagnosis, rationale, ER triage, gaps, plan review, citations | Doha | 12 | 2 | 2026-10-07 | 2026-10-08 | B1 | 15 cases reviewed by clinician; schema valid | In progress | 78.33% | 0% |  |  | 1 | [5 empty] | 4 | 5 | 2 | T | Doha | B0 | B1
B3.1 | Reasoning output schema | Doha | 4 | 1 | 2026-10-07 | 2026-10-07 |  |  | In progress | 80% | 0% |  |  | 2 | [5 empty] | 4 | 4 | 1 | S | Doha
B3.2 | ICD-10 edition rules | Doha | 2 | 1 | 2026-10-07 | 2026-10-07 |  |  | In progress | 50% | 0% |  |  | 2 | [5 empty] | 4 | 4 | 1 | S | Doha
B3.3 | History-scope + citation rules | Doha | 2 | 1 | 2026-10-07 | 2026-10-07 |  |  | In progress | 80% | 0% |  |  | 2 | [5 empty] | 4 | 4 | 1 | S | Doha
B3.4 | 15 clinical test cases | Doha | 4 | 1 | 2026-10-08 | 2026-10-08 |  |  | In progress | 90% | 0% |  |  | 2 | [5 empty] | 5 | 5 | 1 | S | Doha
B2 | Extraction prompts per specialty (ER / OPD / Dental): note fields only, no history | Doha | 14 | 2 | 2026-10-11 | 2026-10-12 | B1 | 100% schema-valid output | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 6 | 7 | 2 | T | Doha | B3 | B1
B2.1 | Remove ICD-10, diagnosis, history from prompts | Doha | 2 | 1 | 2026-10-11 | 2026-10-11 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 6 | 6 | 1 | S | Doha
B2.2 | Strict schemas: ER, OPD, Dental | Doha | 6 | 1 | 2026-10-11 | 2026-10-11 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 6 | 6 | 1 | S | Doha
B2.3 | Schema-validity tests (20 notes per department) | Doha | 6 | 1 | 2026-10-12 | 2026-10-12 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 7 | 7 | 1 | S | Doha
M6 | Carry forward: existing history SQL + scope rules, voice-fill via structuring, consent line | Doha | 9 | 2 | 2026-10-13 | 2026-10-14 | B3, B5 | Voice-fill works in both languages; history never sent to extraction | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 8 | 9 | 2 | T | Doha | B2 | B3 | B5
M6.1 | History sent to reasoning only (existing SQL) | Doha | 4 | 1 | 2026-10-13 | 2026-10-13 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 8 | 8 | 1 | S | Doha
M6.2 | Voice-fill through structuring | Doha | 4 | 1 | 2026-10-13 | 2026-10-13 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 8 | 8 | 1 | S | Doha
M6.3 | Consent line in Conversation Mode | Doha | 1 | 1 | 2026-10-14 | 2026-10-14 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 9 | 9 | 1 | S | Doha
A9 | Run current product on gold set (As-Is baseline) | Doha | 8 | 1 | 2026-10-20 | 2026-10-20 | X5 | Baseline file delivered | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 13 | 13 | 1 | T | Doha | M6 | X5
A9.1 | Run current product on gold set; export results | Doha | 8 | 1 | 2026-10-20 | 2026-10-20 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 13 | 13 | 1 | S | Doha
B6 | Benchmark on gold set: structuring fidelity, extraction (4o mini vs Luna), Terra vs Sol | Doha | 12 | 2 | 2026-10-21 | 2026-10-22 | X5, M4, A3 | Models selected and approved | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 14 | 15 | 2 | T | Doha | A9 | X5 | M4 | A3
B6.1 | Structuring fidelity on gold set | Doha | 4 | 1 | 2026-10-21 | 2026-10-21 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 14 | 14 | 1 | S | Doha
B6.2 | Extraction: GPT-4o mini vs Luna | Doha | 4 | 1 | 2026-10-21 | 2026-10-21 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 14 | 14 | 1 | S | Doha
B6.3 | Reasoning results, escalation share, decision memo | Doha | 4 | 1 | 2026-10-22 | 2026-10-22 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 15 | 15 | 1 | S | Doha
B8 | End-to-end run of new pipeline on gold set | Doha | 4 | 1 | 2026-10-25 | 2026-10-25 | B6 | File delivered to reviewers | Not started | 0% | 0% | [5 empty] | 1 |  |  | 16 | 16 | 1 | T | Doha | B6 | B6
B8.1 | Run new pipeline on gold set; export results | Doha | 4 | 1 | 2026-10-25 | 2026-10-25 |  |  | Not started | 0% | 0% | [5 empty] | 2 |  |  | 16 | 16 | 1 | S | Doha
B9 | Fix gaps found by clinicians; re-run failed cases | Doha | 12 | 2 | 2026-10-28 | 2026-10-29 | X6b | Gate accuracy criteria met | Not started | 0% | 0% | [5 empty] | 1 |  |  | 19 | 20 | 2 | T | Doha | B8 | X6b
B9.1 | Fix failed cases (prompts, triggers, lexicon) | Doha | 6 | 1 | 2026-10-28 | 2026-10-28 |  |  | Not started | 0% | 0% | [5 empty] | 2 |  |  | 19 | 19 | 1 | S | Doha
B9.2 | Re-run affected encounters | Doha | 6 | 2 | 2026-10-28 | 2026-10-29 |  |  | Not started | 0% | 0% | [5 empty] | 2 |  |  | 19 | 20 | 2 | S | Doha
MOHAMED ESSAM — Integration & application
M1 | Clinical AI Gateway (API Management): Entra auth, rate limits, audit log | Mohamed Essam | 12 | 2 | 2026-10-04 | 2026-10-05 | — | All model calls pass through gateway; policies tested | In progress | 0% | 0% |  |  | 1 | [5 empty] | 1 | 2 | 2 | T | Mohamed Essam
M1.1 | API Management instance with VNet | Mohamed Essam | 4 | 1 | 2026-10-04 | 2026-10-04 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 1 | 1 | 1 | S | Mohamed Essam
M1.2 | Policies: Entra ID, rate limits | Mohamed Essam | 4 | 1 | 2026-10-04 | 2026-10-04 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 1 | 1 | 1 | S | Mohamed Essam
M1.3 | Foundry backends; logging without bodies | Mohamed Essam | 4 | 1 | 2026-10-05 | 2026-10-05 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 2 | 2 | 1 | S | Mohamed Essam
M2 | Provider adapter: switch OpenRouter → Foundry by configuration | Mohamed Essam | 6 | 1 | 2026-10-06 | 2026-10-06 | M1 | Provider switch without code change; tests pass | In progress | 0% | 0% |  |  | 1 | [5 empty] | 3 | 3 | 1 | T | Mohamed Essam | M1 | M1
M2.1 | Provider interfaces (LLM, STT) | Mohamed Essam | 4 | 1 | 2026-10-06 | 2026-10-06 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 3 | 3 | 1 | S | Mohamed Essam
M2.2 | Config switch OpenRouter → Foundry | Mohamed Essam | 2 | 1 | 2026-10-06 | 2026-10-06 |  |  | In progress | 0% | 0% | Check |  | 2 | [5 empty] | 3 | 3 | 1 | S | Mohamed Essam
A8 | Build gold set: sample 100 logged sessions (70% Arabic/mixed), de-identify | Mohamed Essam | 8 | 1 | 2026-10-11 | 2026-10-11 | X1 | De-identified package delivered | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 6 | 6 | 1 | T | Mohamed Essam | M2 | X1
A8.1 | Sample 100 sessions; de-identify; package | Mohamed Essam | 8 | 1 | 2026-10-11 | 2026-10-11 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 6 | 6 | 1 | S | Mohamed Essam
M3 | Validation layer: ICD-10 code check, schema, diagnosis–findings consistency, history cross-check, missing-field checklist | Mohamed Essam | 22 | 3 | 2026-10-12 | 2026-10-14 | B1, X2 | All rules tested; invalid output rejected with reason | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 7 | 9 | 3 | T | Mohamed Essam | A8 | B1 | X2
M3.1 | ICD-10 code lookup from HIS master | Mohamed Essam | 4 | 1 | 2026-10-12 | 2026-10-12 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 7 | 7 | 1 | S | Mohamed Essam
M3.2 | Pydantic output schemas | Mohamed Essam | 4 | 1 | 2026-10-12 | 2026-10-12 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 7 | 7 | 1 | S | Mohamed Essam
M3.3 | Consistency rules (laterality, evidence) | Mohamed Essam | 4 | 1 | 2026-10-13 | 2026-10-13 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 8 | 8 | 1 | S | Mohamed Essam
M3.4 | History cross-check + missing-field checklist | Mohamed Essam | 4 | 1 | 2026-10-13 | 2026-10-13 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 8 | 8 | 1 | S | Mohamed Essam
M3.5 | Rule tests | Mohamed Essam | 6 | 1 | 2026-10-14 | 2026-10-14 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 9 | 9 | 1 | S | Mohamed Essam
M7 | Dashboard behind Entra ID; remove transcripts from logs (PHI-safe) | Mohamed Essam | 6 | 1 | 2026-10-15 | 2026-10-15 | M1 | Unauthenticated access returns 401; PHI scan clean | Not started | 0% | 0% |  |  |  | 1 |  |  |  |  | 10 | 10 | 1 | T | Mohamed Essam | M3 | M1
M7.1 | Entra ID on dashboard and admin | Mohamed Essam | 2 | 1 | 2026-10-15 | 2026-10-15 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 10 | 10 | 1 | S | Mohamed Essam
M7.2 | Remove transcripts from logs | Mohamed Essam | 4 | 1 | 2026-10-15 | 2026-10-15 |  |  | Not started | 0% | 0% |  |  |  | 2 |  |  |  |  | 10 | 10 | 1 | S | Mohamed Essam
M4 | Parallel orchestration (extraction ∥ reasoning) + progressive SSE | Mohamed Essam | 14 | 2 | 2026-10-18 | 2026-10-19 | A1, M2, B0, B2, B4, B5, M3 | Stage time ≈ slower branch; merged output passes schema | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 11 | 12 | 2 | T | Mohamed Essam | M7 | A1 | M2 | B0 | B2 | B4 | B5 | M3
M4.1 | Run extraction ∥ reasoning with timeouts | Mohamed Essam | 6 | 1 | 2026-10-18 | 2026-10-18 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 11 | 11 | 1 | S | Mohamed Essam
M4.2 | Merge → validation → escalation | Mohamed Essam | 4 | 2 | 2026-10-18 | 2026-10-19 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 11 | 12 | 2 | S | Mohamed Essam
M4.3 | SSE events to the UI | Mohamed Essam | 4 | 1 | 2026-10-19 | 2026-10-19 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 12 | 12 | 1 | S | Mohamed Essam
M5 | UI: progressive results, citations, cautions, re-run reasoning, speaker confirmation | Mohamed Essam | 10 | 2 | 2026-10-20 | 2026-10-21 | M4 | All flows usable in staging | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 13 | 14 | 2 | T | Mohamed Essam | M4 | M4
M5.1 | Progressive rendering | Mohamed Essam | 2 | 1 | 2026-10-20 | 2026-10-20 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 13 | 13 | 1 | S | Mohamed Essam
M5.2 | Citation click-through | Mohamed Essam | 2 | 1 | 2026-10-20 | 2026-10-20 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 13 | 13 | 1 | S | Mohamed Essam
M5.3 | Caution banners + re-run reasoning | Mohamed Essam | 4 | 1 | 2026-10-20 | 2026-10-20 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 13 | 13 | 1 | S | Mohamed Essam
M5.4 | Speaker confirmation + Arabic RTL check | Mohamed Essam | 2 | 1 | 2026-10-21 | 2026-10-21 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 14 | 14 | 1 | S | Mohamed Essam
M8 | Functional regression test against current product | Mohamed Essam | 12 | 2 | 2026-10-22 | 2026-10-25 | M5, M6 | No open S1/S2 defects | Not started | 0% | 0% |  |  |  |  | 1 | 1 |  |  | 15 | 16 | 2 | T | Mohamed Essam | M5 | M5 | M6
M8.1 | 30 regression scenarios | Mohamed Essam | 8 | 1 | 2026-10-22 | 2026-10-22 |  |  | Not started | 0% | 0% |  |  |  |  | 2 |  |  |  | 15 | 15 | 1 | S | Mohamed Essam
M8.2 | Defect triage and retest | Mohamed Essam | 4 | 1 | 2026-10-25 | 2026-10-25 |  |  | Not started | 0% | 0% | [5 empty] | 2 |  |  | 16 | 16 | 1 | S | Mohamed Essam
M9 | Fix penetration-test findings | Mohamed Essam | 12 | 2 | 2026-10-26 | 2026-10-27 | X7 | Security sign-off | Not started | 0% | 0% | [5 empty] | 1 |  |  | 17 | 18 | 2 | T | Mohamed Essam | M8 | X7
M9.1 | Fix high / medium findings | Mohamed Essam | 8 | 1 | 2026-10-26 | 2026-10-26 |  |  | Not started | 0% | 0% | [5 empty] | 2 |  |  | 17 | 17 | 1 | S | Mohamed Essam
M9.2 | Retest with security team | Mohamed Essam | 4 | 1 | 2026-10-27 | 2026-10-27 |  |  | Not started | 0% | 0% | [5 empty] | 2 |  |  | 18 | 18 | 1 | S | Mohamed Essam
CLINICAL, SECURITY & UAT — outside the AI team
X10 | Clinical Lead reviews red-flag lexicon (Arabic / English) | Clinical Lead | 1 | 3 | 2026-10-07 | 2026-10-11 | B0 | Lexicon signed off | Not started | 0% | 0% |  |  | 1 | 1 |  |  |  |  | 4 | 6 | 3 | T | Ext |  | B0
X5 | Clinicians annotate 100 encounters (fields, ICD-10, diagnosis) | Clinical reviewers | 1 | 6 | 2026-10-12 | 2026-10-19 | A8 | 100 encounters annotated and frozen | Not started | 0% | 0% |  |  |  | 1 | 1 |  |  |  | 7 | 12 | 6 | T | Ext |  | A8
X6a | Clinicians score As-Is baseline outputs | Clinical reviewers | 1 | 2 | 2026-10-21 | 2026-10-22 | A9 | Baseline scores complete | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 14 | 15 | 2 | T | Ext |  | A9
X7 | Penetration test on staging (gateway, endpoints, app) | Security team | 1 | 3 | 2026-10-20 | 2026-10-22 | M4, M7, A4 | Findings report delivered | Not started | 0% | 0% |  |  |  |  | 1 |  |  |  | 13 | 15 | 3 | T | Ext |  | M4 | M7 | A4
X6b | Clinicians score new-pipeline outputs | Clinical reviewers | 1 | 2 | 2026-10-26 | 2026-10-27 | B8, X6a | Scores complete | Not started | 0% | 0% | [5 empty] | 1 |  |  | 17 | 18 | 2 | T | Ext |  | B8 | X6a
X9 | Doctor training and quick guide | Product Owner | 1 | 2 | 2026-10-22 | 2026-10-25 | M5 | Pilot doctors trained | Not started | 0% | 0% |  |  |  |  | 1 | 1 |  |  | 15 | 16 | 2 | T | Ext |  | M5
X8 | UAT with doctors (ER, OPD, Dental; Arabic and English) | Doctors + Clinical Lead | 1 | 3 | 2026-10-26 | 2026-10-28 | M8 | UAT sign-off | Not started | 0% | 0% | [5 empty] | 1 |  |  | 17 | 19 | 3 | T | Ext |  | M8
GATE, PILOT & GO-LIVE
G1 | Go-live gate: accuracy, load, security and UAT criteria met | Steering + Clinical Lead | 2 | 1 | 2026-11-01 | 2026-11-01 | B9, A6, M9, X3, X4, X8, X10 | Decision recorded | Not started | 0% | 0% | [6 empty] | 1 |  | 21 | 21 | 1 | T | Ext |  | B9 | A6 | M9 | X3 | X4 | X8 | X10
P1 | Controlled pilot at one site (rollback ready) | PM + Clinical Lead | 4 | 4 | 2026-11-02 | 2026-11-05 | G1, X9 | Pilot stable for 4 days | Not started | 0% | 0% | [6 empty] | 1 |  | 22 | 25 | 4 | T | Ext |  | G1 | X9
P2 | Go / no-go decision and production cutover | Steering | 4 | 1 | 2026-11-08 | 2026-11-08 | P1 | Production live | Not started | 0% | 0% | [7 empty] | 1 | 26 | 26 | 1 | T | Ext |  | P1
Flags
Done — finished (100%)
Check — status and % do not match
Late — end date passed, not 100%
Blocked — see Notes / blockers
Yellow — update in the meeting
Formulas:
Start = C5+INT(([SD]-1)/5)*7+MOD([SD]-1,5)
End = C5+INT(([ED]-1)/5)*7+MOD([ED]-1,5)
Note on C8: Go-live date agreed in the 6-week plan (v3.4).
Note on D13: AI-engineer rows: estimated hours (editable on subtasks). External rows: effort only; it does not change the schedule.
Note on E13: Engineering tasks: hours ÷ 8, rounded up. External tasks: elapsed working days (editable).
Note on L13: Share of checklist items marked Yes on the Checklist sheet.

## Checklist
MedVoice v3.4 — Checklist per subtask
Mark each item Yes only when the evidence exists. The Checklist % on the Tracker updates automatically. Filter by Owner or Task to run your own list.
Items done |  | 0 of 179 | Completion |  | 0%
Owner | Task ID | Task | Subtask ID | Subtask | # | Check item | Evidence to show | Done? | Checked by | Date | Comment
PRE-REQUISITES — outside the AI team
Compliance | X1 | Approve use of de-identified logged sessions as the gold set | X1 | — | 1 | Request submitted with scope, de-identification method and access list | Request reference | No
Compliance | X1 |  | X1 |  | 2 | Conditions of use recorded | Approval letter | No
Compliance | X1 |  | X1 |  | 3 | Approval shared with AI team | Email / Teams message | No
Coding team | X2 | Export ICD-10 code master from the HIS coding system | X2 | — | 1 | ICD-10 file exported from HIS coding system | codes.csv | No
Coding team | X2 |  | X2 |  | 2 | Edition and version stated (e.g. ICD-10-AM) | File header / note | No
Coding team | X2 |  | X2 |  | 3 | File received by Mohamed | Message confirming receipt | No
Compliance | X3 | Confirm residency: Foundry region; continued use of Munsit and Voxtral APIs | X3 | — | 1 | Foundry region approved for patient text | Written decision | No
Compliance | X3 |  | X3 |  | 2 | Continued use of Munsit and Voxtral APIs approved | Written decision | No
Compliance | X3 |  | X3 |  | 3 | Conditions shared with AI team | Email | No
Steering | X4 | Sign acceptance thresholds and pilot site | X4 | — | 1 | Acceptance thresholds reviewed (design 14.3) | Signed sheet | No
Steering | X4 |  | X4 |  | 2 | Pilot site and doctors named | List of names | No
Steering | X4 |  | X4 |  | 3 | Signed by steering | Signature / minutes | No
AHMED HAMDY — Platform & performance
Ahmed Hamdy | A1 | Fix LLM concurrency: shared async client, 45 s timeout, backoff + jitter, per-model limits, async streaming | A1.1 | Shared async client + 45 s timeout, no hidden retries | 1 | One AsyncOpenAI client created at startup (lifespan) | Code: no client created per request | No
Ahmed Hamdy | A1 |  | A1.1 |  | 2 | Timeout 45 s, max_retries=0 set | Config / code | No
Ahmed Hamdy | A1 |  | A1.1 |  | 3 | Unit tests pass | CI run | No
Ahmed Hamdy | A1 |  | A1.2 | Async streaming for refine / translate | 1 | Streaming uses async for on an async stream | Code diff | No
Ahmed Hamdy | A1 |  | A1.2 |  | 2 | No blocking loop inside async generator | Code review note | No
Ahmed Hamdy | A1 |  | A1.3 | Backoff + jitter on 429/5xx; remove key rotation | 1 | Retry only on 429, 5xx, timeouts; honours Retry-After | Code + test | No
Ahmed Hamdy | A1 |  | A1.3 |  | 2 | Max 4 attempts with jitter | Config | No
Ahmed Hamdy | A1 |  | A1.3 |  | 3 | Key rotation on 429 removed | Code diff | No
Ahmed Hamdy | A1 |  | A1.4 | Per-model concurrency limits (semaphores) | 1 | Semaphore per model; limit in config | Config file | No
Ahmed Hamdy | A1 |  | A1.4 |  | 2 | Limit sized with Little’s law | Calculation note | No
Ahmed Hamdy | A1 |  | A1.5 | Test: 30 parallel analyses | 1 | 30 parallel analyses complete | Test output | No
Ahmed Hamdy | A1 |  | A1.5 |  | 2 | Mocked 429s retried ≤ 3 times each | Test log | No
Ahmed Hamdy | A1 |  | A1.5 |  | 3 | Event-loop lag < 50 ms | Measurement | No
Ahmed Hamdy | A2 | Azure foundation: Key Vault, managed identities, private endpoints, App Insights | A2.1 | Key Vault; move all secrets | 1 | Key Vault created; access via RBAC | Azure portal | No
Ahmed Hamdy | A2 |  | A2.1 |  | 2 | All secrets moved; none in code or env files | Repo scan | No
Ahmed Hamdy | A2 |  | A2.2 | Managed identities + RBAC | 1 | User-assigned managed identity created and attached to app | Azure portal | No
Ahmed Hamdy | A2 |  | A2.2 |  | 2 | Roles granted (Key Vault Secrets User, Foundry user) | Role assignments | No
Ahmed Hamdy | A2 |  | A2.3 | Private endpoints + DNS (Foundry, Key Vault) | 1 | Private endpoints for Foundry and Key Vault | Azure portal | No
Ahmed Hamdy | A2 |  | A2.3 |  | 2 | Private DNS resolves to private IP from app subnet | nslookup output | No
Ahmed Hamdy | A2 |  | A2.3 |  | 3 | Public network access disabled | Resource settings | No
Ahmed Hamdy | A2 |  | A2.4 | App Insights, no patient text in logs | 1 | App Insights connected (OpenTelemetry) | Traces visible | No
Ahmed Hamdy | A2 |  | A2.4 |  | 2 | No transcript or note text in logs | Log sample check | No
Ahmed Hamdy | B5 | Incremental structuring: structure each transcript segment live, consolidate at end | B5.1 | Structure each final transcript segment with running context | 1 | Each final transcript segment structured with running context | Demo / log | No
Ahmed Hamdy | B5 |  | B5.1 |  | 2 | Speaker labels preserved per segment | Sample output | No
Ahmed Hamdy | B5 |  | B5.2 | Consolidation pass when dictation stops | 1 | Consolidation runs on stop | Code + demo | No
Ahmed Hamdy | B5 |  | B5.2 |  | 2 | Final note ready ≤ 3 s after stop | Timing log | No
Ahmed Hamdy | B5 |  | B5.3 | Compare with one-shot on 10 transcripts | 1 | 10 transcripts compared with one-shot | Comparison sheet | No
Ahmed Hamdy | B5 |  | B5.3 |  | 2 | No omissions or added detail vs one-shot | Reviewer note | No
Ahmed Hamdy | B4 | Reasoning router: rule-based triggers, GPT-5.6 Terra default, one-step escalation to Sol, audit | B4.1 | Trigger rules as a pure function | 1 | Triggers implemented as a pure function | Code | No
Ahmed Hamdy | B4 |  | B4.1 |  | 2 | Each trigger has a unit test | CI run | No
Ahmed Hamdy | B4 |  | B4.2 | Terra default; one escalation to Sol | 1 | Terra is default for every encounter | Config | No
Ahmed Hamdy | B4 |  | B4.2 |  | 2 | One escalation to Sol on validation failure; never more | Test | No
Ahmed Hamdy | B4 |  | B4.3 | Audit record + unit tests | 1 | Audit record per routing decision (signals, tier, reason) | Log sample | No
Ahmed Hamdy | B4 |  | B4.3 |  | 2 | Tests pass | CI run | No
Ahmed Hamdy | A4 | CI/CD pipeline and staging environment | A4.1 | CI pipeline: lint, test, build, push | 1 | Pipeline: lint → tests → build → push to registry | Pipeline run | No
Ahmed Hamdy | A4 |  | A4.1 |  | 2 | Pipeline green on main | Screenshot | No
Ahmed Hamdy | A4 |  | A4.2 | Staging environment | 1 | Staging created from same configuration as production | Resource list | No
Ahmed Hamdy | A4 |  | A4.2 |  | 2 | Staging reachable only on private network | Access test | No
Ahmed Hamdy | A4 |  | A4.3 | Smoke test + approval gate to production | 1 | Smoke test /health after deploy | Pipeline log | No
Ahmed Hamdy | A4 |  | A4.3 |  | 2 | Manual approval required for production | Pipeline setting | No
Ahmed Hamdy | A3 | Deploy Foundry models: GPT-4o mini, GPT-5.6 Luna / Terra / Sol, structuring LLM | A3.1 | Deploy GPT-4o mini, Luna, Terra, Sol, DeepSeek V3 | 1 | GPT-4o mini, GPT-5.6 Luna, Terra, Sol, DeepSeek V3 deployed in approved region | Foundry deployments list | No
Ahmed Hamdy | A3 |  | A3.2 | Record quotas; add to config | 1 | Quotas (TPM/RPM) recorded per model | Quota table | No
Ahmed Hamdy | A3 |  | A3.2 |  | 2 | Deployment names in config | Config file | No
Ahmed Hamdy | A3 |  | A3.3 | Strict-JSON smoke test; content-filter check | 1 | Each model returns valid strict JSON | Smoke-test output | No
Ahmed Hamdy | A3 |  | A3.3 |  | 2 | Content filter does not block 20 clinical samples | Test log | No
Ahmed Hamdy | A5 | Load-test harness for WebSocket + SSE sessions | A5.1 | Locust session script (audio stream + SSE) | 1 | Locust script streams audio in real time | Script in repo | No
Ahmed Hamdy | A5 |  | A5.1 |  | 2 | Script reads SSE until done | Demo run | No
Ahmed Hamdy | A5 |  | A5.2 | Export timings per session | 1 | Timings exported per session (first partial, final, first SSE, total) | CSV sample | No
Ahmed Hamdy | A7 | Resilience: health checks, circuit breakers, model fallback, admission control | A7.1 | Health and readiness probes | 1 | /health and /ready per dependency | Endpoint responses | No
Ahmed Hamdy | A7 |  | A7.1 |  | 2 | /ready returns 503 when a dependency is down | Test | No
Ahmed Hamdy | A7 |  | A7.2 | Circuit breaker per provider | 1 | Circuit breaker per provider (5 failures / 30 s) | Code + test | No
Ahmed Hamdy | A7 |  | A7.2 |  | 2 | Half-open probe recovers automatically | Test log | No
Ahmed Hamdy | A7 |  | A7.3 | Model fallbacks (4o mini ↔ Luna, Terra → Sol) | 1 | Extraction fallback GPT-4o mini ↔ Luna works | Test | No
Ahmed Hamdy | A7 |  | A7.3 |  | 2 | Reasoning fallback Terra → Sol works | Test | No
Ahmed Hamdy | A7 |  | A7.4 | Admission control (503 + Retry-After) | 1 | Max active sessions per replica in config | Config | No
Ahmed Hamdy | A7 |  | A7.4 |  | 2 | Overload returns 503 + Retry-After | Load-test log | No
Ahmed Hamdy | A6 | Load test 1→50 sessions; tune limits; confirm p95 latency and 429 rate | A6.1 | Ramp 1 → 50 sessions per language | 1 | Ramp 1 → 5 → 10 → 20 → 50 per language completed | Locust report | No
Ahmed Hamdy | A6 |  | A6.1 |  | 2 | p50 / p95 / 429 rate recorded per step | Report table | No
Ahmed Hamdy | A6 |  | A6.2 | Accuracy check at peak (20 encounters) | 1 | 20 gold encounters replayed at peak | Run log | No
Ahmed Hamdy | A6 |  | A6.2 |  | 2 | Accuracy loss < 2 points vs low load | Comparison | No
Ahmed Hamdy | A6 |  | A6.3 | Tune limits; capacity report | 1 | Limits tuned | Config diff | No
Ahmed Hamdy | A6 |  | A6.3 |  | 2 | Capacity report signed | Report | No
DOHA — Clinical AI
Doha | B1 | Structuring prompt + schema: sections, translation, speaker labels with confidence, no-inference rules, routing signals | B1.1 | Structured-note JSON schema | 1 | JSON schema: sections, speaker, confidence, segment IDs, routing signals | Schema file | No
Doha | B1 |  | B1.1 |  | 2 | Clinical Lead reviewed schema | Approval | No
Doha | B1 |  | B1.2 | Prompt: no-inference + translation rules | 1 | No-inference rule in prompt (never add, infer, sharpen) | Prompt file | No
Doha | B1 |  | B1.2 |  | 2 | Arabic/mixed → English translation rule | Prompt file | No
Doha | B1 |  | B1.3 | Arabic / mixed few-shot examples | 1 | 6–8 few-shot examples incl. negation and laterality | Prompt file | No
Doha | B1 |  | B1.4 | 20 fidelity tests | 1 | 20 fidelity tests written | Test file | No
Doha | B1 |  | B1.4 |  | 2 | All 20 pass | CI run | No
Doha | B0 | Keep term correction before structuring; add red-flag lexicon for routing | B0.1 | Keep term correction before structuring | 1 | Term correction runs before structuring | Code / pipeline order | No
Doha | B0 |  | B0.2 | Red-flag lexicon file + routing signal | 1 | Red-flag lexicon file committed (Arabic + English) | File in repo | No
Doha | B0 |  | B0.2 |  | 2 | red_flags emitted in routing signals | Sample output | No
Doha | B3 | Reasoning prompt: ICD-10 (edition stated), diagnosis, rationale, ER triage, gaps, plan review, citations | B3.1 | Reasoning output schema | 1 | Schema: ICD-10 + evidence, diagnosis, rationale, triage, gaps, plan review, history flags | Schema file | No
Doha | B3 |  | B3.2 | ICD-10 edition rules per country | 1 | ICD-10 edition set per country in config | Config | No
Doha | B3 |  | B3.2 |  | 2 | Prompt names the edition | Prompt file | No
Doha | B3 |  | B3.3 | History-scope + citation rules | 1 | History informs only ICD-10, diagnosis, rationale | Prompt + test | No
Doha | B3 |  | B3.3 |  | 2 | Every output item cites a note sentence | Sample output | No
Doha | B3 |  | B3.4 | 15 clinical test cases | 1 | 15 test cases incl. history conflict and red flags | Test file | No
Doha | B3 |  | B3.4 |  | 2 | Clinician reviewed results | Review note | No
Doha | B2 | Extraction prompts per specialty (ER / OPD / Dental): note fields only, no history | B2.1 | Remove ICD-10, diagnosis, history from prompts | 1 | ICD-10, diagnosis and history fields removed from extraction prompts | Prompt diff | No
Doha | B2 |  | B2.2 | Strict schemas: ER, OPD, Dental | 1 | Strict schemas for ER, OPD, Dental | Schema files | No
Doha | B2 |  | B2.2 |  | 2 | Allowed values enforced (e.g. Dental consent) | Schema | No
Doha | B2 |  | B2.3 | Schema-validity tests (20 notes per department) | 1 | 20 notes per department tested | Test file | No
Doha | B2 |  | B2.3 |  | 2 | 100% schema-valid output | CI run | No
Doha | M6 | Carry forward: existing history SQL + scope rules, voice-fill via structuring, consent line | M6.1 | History sent to reasoning only (existing SQL) | 1 | History sent only to reasoning, never to extraction | Code + test | No
Doha | M6 |  | M6.1 |  | 2 | Existing SQL source reused | Code | No
Doha | M6 |  | M6.2 | Voice-fill through structuring | 1 | Voice-fill answer passes term correction + structuring | Demo | No
Doha | M6 |  | M6.2 |  | 2 | Works in Arabic and English | Test log | No
Doha | M6 |  | M6.3 | Consent line in Conversation Mode | 1 | Consent line still plays once in Conversation Mode | Demo | No
Doha | A9 | Run current product on gold set (As-Is baseline) | A9.1 | Run current product on gold set; export results | 1 | Current product run on all 100 gold transcripts | baseline.jsonl | No
Doha | A9 |  | A9.1 |  | 2 | File delivered to reviewers | Message | No
Doha | B6 | Benchmark on gold set: structuring fidelity, extraction (4o mini vs Luna), Terra vs Sol | B6.1 | Structuring fidelity on gold set | 1 | Structuring fidelity measured (omissions, additions, negation, laterality) | Results sheet | No
Doha | B6 |  | B6.2 | Extraction: GPT-4o mini vs Luna | 1 | Field accuracy per department: GPT-4o mini vs Luna | Results sheet | No
Doha | B6 |  | B6.2 |  | 2 | Winner and fallback chosen | Decision memo | No
Doha | B6 |  | B6.3 | Reasoning results, escalation share, decision memo | 1 | Terra results and escalation share recorded | Results sheet | No
Doha | B6 |  | B6.3 |  | 2 | Decision memo approved by architect | Approval | No
Doha | B8 | End-to-end run of new pipeline on gold set | B8.1 | Run new pipeline on gold set; export results | 1 | New pipeline run on all 100 gold transcripts | new_pipeline.jsonl | No
Doha | B8 |  | B8.1 |  | 2 | File delivered to reviewers | Message | No
Doha | B9 | Fix gaps found by clinicians; re-run failed cases | B9.1 | Fix failed cases (prompts, triggers, lexicon) | 1 | Failed cases fixed (prompts, triggers, lexicon) | Change log | No
Doha | B9 |  | B9.2 | Re-run affected encounters | 1 | Affected encounters re-run | Run log | No
Doha | B9 |  | B9.2 |  | 2 | Gate accuracy criteria met | Score summary | No
MOHAMED ESSAM — Integration & application
Mohamed Essam | M1 | Clinical AI Gateway (API Management): Entra auth, rate limits, audit log | M1.1 | API Management instance with VNet | 1 | API Management created with VNet support | Azure portal | No
Mohamed Essam | M1 |  | M1.1 |  | 2 | Reachable only from private network | Access test | No
Mohamed Essam | M1 |  | M1.2 | Policies: Entra ID, rate limits | 1 | validate-jwt (Entra ID) policy active | Policy file + test | No
Mohamed Essam | M1 |  | M1.2 |  | 2 | Rate-limit policy active | 429 test | No
Mohamed Essam | M1 |  | M1.3 | Foundry backends; logging without bodies | 1 | Backends for each Foundry model use managed identity | Policy / backend config | No
Mohamed Essam | M1 |  | M1.3 |  | 2 | Logs exclude request bodies | Log sample | No
Mohamed Essam | M2 | Provider adapter: switch OpenRouter → Foundry by configuration | M2.1 | Provider interfaces (LLM, STT) | 1 | LLMProvider and STTProvider interfaces in code | Code | No
Mohamed Essam | M2 |  | M2.2 | Config switch OpenRouter → Foundry | 1 | Switch OpenRouter → Foundry by config only | Config + demo | No
Mohamed Essam | M2 |  | M2.2 |  | 2 | Tests pass after switch | CI run | No
Mohamed Essam | A8 | Build gold set: sample 100 logged sessions (70% Arabic/mixed), de-identify | A8.1 | Sample 100 sessions; de-identify; package | 1 | 100 sessions sampled: 70% Arabic/mixed, all departments, both modes | Sampling sheet | No
Mohamed Essam | A8 |  | A8.1 |  | 2 | Names, IDs, dates, phones removed | De-identification check | No
Mohamed Essam | A8 |  | A8.1 |  | 3 | Package delivered to reviewers | Storage link | No
Mohamed Essam | M3 | Validation layer: ICD-10 code check, schema, diagnosis–findings consistency, history cross-check, missing-field checklist | M3.1 | ICD-10 code lookup from HIS master | 1 | ICD-10 code master loaded as lookup | Code + data file | No
Mohamed Essam | M3 |  | M3.1 |  | 2 | Invalid code rejected | Test | No
Mohamed Essam | M3 |  | M3.2 | Pydantic output schemas | 1 | Pydantic schemas for extraction and reasoning outputs | Code | No
Mohamed Essam | M3 |  | M3.2 |  | 2 | Invalid output rejected with reason | Test | No
Mohamed Essam | M3 |  | M3.3 | Consistency rules (laterality, evidence) | 1 | Laterality mismatch flagged | Test | No
Mohamed Essam | M3 |  | M3.3 |  | 2 | Diagnosis without evidence flagged | Test | No
Mohamed Essam | M3 |  | M3.4 | History cross-check + missing-field checklist | 1 | History cross-check reused and working | Test | No
Mohamed Essam | M3 |  | M3.4 |  | 2 | Missing-field checklist generated deterministically | Test | No
Mohamed Essam | M3 |  | M3.5 | Rule tests | 1 | Unit test per validation rule | CI run | No
Mohamed Essam | M7 | Dashboard behind Entra ID; remove transcripts from logs (PHI-safe) | M7.1 | Entra ID on dashboard and admin | 1 | Dashboard and admin require Entra sign-in | 401 test without login | No
Mohamed Essam | M7 |  | M7.1 |  | 2 | Admin role enforced | Role test | No
Mohamed Essam | M7 |  | M7.2 | Remove transcripts from logs | 1 | Transcripts and notes no longer written to JSONL or logs | Log / file check | No
Mohamed Essam | M4 | Parallel orchestration (extraction ∥ reasoning) + progressive SSE | M4.1 | Run extraction ∥ reasoning with timeouts | 1 | Extraction and reasoning run in parallel (TaskGroup) | Code + timing log | No
Mohamed Essam | M4 |  | M4.1 |  | 2 | Per-branch timeout set | Config | No
Mohamed Essam | M4 |  | M4.2 | Merge → validation → escalation | 1 | Merge → validation → one escalation | Code + test | No
Mohamed Essam | M4 |  | M4.2 |  | 2 | Merged output passes schema | Test | No
Mohamed Essam | M4 |  | M4.3 | SSE events to the UI | 1 | SSE events: structured, fields, reasoning, cautions, done | Event log | No
Mohamed Essam | M5 | UI: progressive results, citations, cautions, re-run reasoning, speaker confirmation | M5.1 | Progressive rendering | 1 | Fields render first; reasoning appears when ready | Demo | No
Mohamed Essam | M5 |  | M5.2 | Citation click-through | 1 | Each ICD-10 / diagnosis item links to its note sentence | Demo | No
Mohamed Essam | M5 |  | M5.3 | Caution banners + re-run reasoning | 1 | Caution banners next to affected fields | Demo | No
Mohamed Essam | M5 |  | M5.3 |  | 2 | Re-run reasoning button works | Demo | No
Mohamed Essam | M5 |  | M5.4 | Speaker confirmation + Arabic RTL check | 1 | Low-confidence speaker labels can be confirmed | Demo | No
Mohamed Essam | M5 |  | M5.4 |  | 2 | Arabic text renders right-to-left | Screenshot | No
Mohamed Essam | M8 | Functional regression test against current product | M8.1 | 30 regression scenarios | 1 | 30 scenarios executed (department × mode × language) | Regression sheet | No
Mohamed Essam | M8 |  | M8.1 |  | 2 | Results compared with current product | Sheet | No
Mohamed Essam | M8 |  | M8.2 | Defect triage and retest | 1 | All defects triaged; no open S1/S2 | Defect list | No
Mohamed Essam | M9 | Fix penetration-test findings | M9.1 | Fix high / medium findings | 1 | All high and medium pen-test findings fixed | Fix list | No
Mohamed Essam | M9 |  | M9.2 | Retest with security team | 1 | Security team retest passed | Retest report | No
CLINICAL, SECURITY & UAT — outside the AI team
Clinical Lead | X10 | Clinical Lead reviews red-flag lexicon (Arabic / English) | X10 | — | 1 | Arabic and English red-flag terms reviewed | Reviewed lexicon file | No
Clinical Lead | X10 |  | X10 |  | 2 | False triggers removed | Change log | No
Clinical Lead | X10 |  | X10 |  | 3 | Lexicon signed off | Clinical Lead approval | No
Clinical reviewers | X5 | Clinicians annotate 100 encounters (fields, ICD-10, diagnosis) | X5 | — | 1 | 100 encounters annotated: fields, ICD-10, diagnosis | gold.jsonl (100 records) | No
Clinical reviewers | X5 |  | X5 |  | 2 | 10% second-reviewer spot check done | Spot-check log | No
Clinical reviewers | X5 |  | X5 |  | 3 | Gold set frozen and versioned | File version / hash | No
Clinical reviewers | X6a | Clinicians score As-Is baseline outputs | X6a | — | 1 | All baseline outputs scored with rubric | Score sheet (100 rows) | No
Clinical reviewers | X6a |  | X6a |  | 2 | Scores shared with Doha | File link | No
Security team | X7 | Penetration test on staging (gateway, endpoints, app) | X7 | — | 1 | Gateway, app, dashboard and endpoints tested on staging | Test scope | No
Security team | X7 |  | X7 |  | 2 | OWASP API Top 10 covered | Checklist | No
Security team | X7 |  | X7 |  | 3 | Findings report with severities delivered | Report | No
Clinical reviewers | X6b | Clinicians score new-pipeline outputs | X6b | — | 1 | All new-pipeline outputs scored with same rubric | Score sheet (100 rows) | No
Clinical reviewers | X6b |  | X6b |  | 2 | Comparison with baseline produced | Summary table | No
Product Owner | X9 | Doctor training and quick guide | X9 | — | 1 | One-page quick guide ready | PDF guide | No
Product Owner | X9 |  | X9 |  | 2 | Session held per department | Attendance list | No
Doctors + Clinical Lead | X8 | UAT with doctors (ER, OPD, Dental; Arabic and English) | X8 | — | 1 | 15 UAT scenarios executed (ER/OPD/Dental, both languages, both modes) | UAT sheet | No
Doctors + Clinical Lead | X8 |  | X8 |  | 2 | Issues logged and triaged | Issue list | No
Doctors + Clinical Lead | X8 |  | X8 |  | 3 | UAT signed off | Signature | No
GATE, PILOT & GO-LIVE
Steering + Clinical Lead | G1 | Go-live gate: accuracy, load, security and UAT criteria met | G1 | — | 1 | Accuracy criteria met (fields ≥ baseline; diagnosis, ICD-10, gaps > baseline) | Score summary | No
Steering + Clinical Lead | G1 |  | G1 |  | 2 | Load, security, UAT and residency criteria met | Reports | No
Steering + Clinical Lead | G1 |  | G1 |  | 3 | Go / no-go decision recorded | Minutes | No
PM + Clinical Lead | P1 | Controlled pilot at one site (rollback ready) | P1 | — | 1 | Pilot doctors enabled; rollback tested | Feature-flag screenshot | No
PM + Clinical Lead | P1 |  | P1 |  | 2 | Daily review held (accept/edit/reject, latency, errors) | Daily notes | No
PM + Clinical Lead | P1 |  | P1 |  | 3 | No open critical issue after 4 days | Issue list | No
Steering | P2 | Go / no-go decision and production cutover | P2 | — | 1 | Go / no-go meeting held | Minutes | No
Steering | P2 |  | P2 |  | 2 | Production switched on; rollback on standby | Feature flag + monitoring screenshot | No