## Sheet1
Detailed Plan — tasks and subtasks
Bold = task (scheduled). Indented = subtask (hours). Yellow = editable. Weekly columns show engineering hours per task; external rows show elapsed days.
ID | Task / subtask | Owner | Hours | Days | Depends on | After (same engineer) | Start day | End day | Start | End | Done when | Refs | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | Level | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10
PRE-REQUISITES — start on day 1 (owners outside the AI team)
X1 | Approve use of de-identified logged sessions as clinical gold set | Compliance | 8 | 5 | — (day 1) | — | 1 | 5 | 2026-09-30 | 2026-10-04 | [14 empty] | Task | bar: W1
X1.1 | Submit data-use request | Compliance | 4 |  |  |  | 1 | 5 | 2026-09-30 | 2026-10-04 | Request submitted. | R24 | [12 empty] | Sub
X1.2 | Review and approval | Compliance | 4 |  |  |  | 1 | 5 | 2026-09-30 | 2026-10-04 | Approval letter. | R32 | [12 empty] | Sub
X2 | Approve recording consent for a speech test set (audio) | Compliance | 10 | 10 | — (day 1) | — | 1 | 10 | 2026-09-30 | 2026-10-11 | [14 empty] | Task | bar: W1 to W2
X2.1 | Consent form + script | Compliance | 6 |  |  |  | 1 | 10 | 2026-09-30 | 2026-10-11 | Form approved. | R32 | [12 empty] | Sub
X2.2 | Approval | Compliance | 4 |  |  |  | 1 | 10 | 2026-09-30 | 2026-10-11 | Approval letter. | R32 | [12 empty] | Sub
X3 | Export ICD-10 code master from the HIS coding system | Coding team | 6 | 3 | — (day 1) | — | 1 | 3 | 2026-09-30 | 2026-10-02 | [14 empty] | Task | bar: W1
X3.1 | Export ICD-10 master | Coding team | 6 |  |  |  | 1 | 3 | 2026-09-30 | 2026-10-02 | File delivered. | R30 | [12 empty] | Sub
X4 | Data-residency approval: Foundry, Munsit private, Google fallback | Compliance | 16 | 20 | — (day 1) | — | 1 | 20 | 2026-09-30 | 2026-10-25 | [14 empty] | Task | bar: W1 to W4
X4.1 | Residency review | Compliance | 16 |  |  |  | 1 | 20 | 2026-09-30 | 2026-10-25 | Written decision. | R12, R20 | [12 empty] | Sub
X5 | Munsit Enterprise agreement and private-deployment package | Vendor / Procurement | 24 | 20 | — (day 1) | — | 1 | 20 | 2026-09-30 | 2026-10-25 | [14 empty] | Task | bar: W1 to W4
X5.1 | Negotiate and sign agreement | Vendor / Procurement | 24 |  |  |  | 1 | 20 | 2026-09-30 | 2026-10-25 | Signed agreement + package. | R33 | [12 empty] | Sub
X6 | GPU quota approval (A10 + A100 80GB / H100) | Cloud admin | 4 | 10 | — (day 1) | — | 1 | 10 | 2026-09-30 | 2026-10-11 | [14 empty] | Task | bar: W1 to W2
X6.1 | Request GPU quota | Cloud admin | 4 |  |  |  | 1 | 10 | 2026-09-30 | 2026-10-11 | Quota granted. | R14 | [12 empty] | Sub
X7 | Sign acceptance thresholds; peak-load forecast per site | Steering + Operations | 8 | 3 | — (day 1) | — | 1 | 3 | 2026-09-30 | 2026-10-02 | [14 empty] | Task | bar: W1
X7.1 | Thresholds + peak forecast | Steering + Operations | 8 |  |  |  | 1 | 3 | 2026-09-30 | 2026-10-02 | Signed sheet. | R32 | [12 empty] | Sub
X8 | HIS interface specification and test endpoint | HIS team | 16 | 5 | — (day 1) | — | 1 | 5 | 2026-09-30 | 2026-10-04 | [14 empty] | Task | bar: W1
X8.1 | HIS interface spec | HIS team | 16 |  |  |  | 1 | 5 | 2026-09-30 | 2026-10-04 | Spec + endpoint available. | R29 | [12 empty] | Sub
AHMED HAMDY — Platform, speech & performance
A1 | Fix LLM concurrency: shared async client, timeouts, backoff + jitter, per-model limits, async streaming | Ahmed Hamdy | 32 | 4 | — (day 1) | — | 1 | 4 | 2026-09-30 | 2026-10-03 |  |  | W1: 32 | Task
A1.1 | Shared async client per process | Ahmed Hamdy | 8 | 1 |  |  | 1 | 1 | 2026-09-30 | 2026-09-30 | No OpenAI(...) constructed per request; one connection pool per worker. | R1, R2, R3 | [12 empty] | Sub
A1.2 | Async streaming for refine / translate | Ahmed Hamdy | 6 | 0.75 |  |  | 2 | 2 | 2026-10-01 | 2026-10-01 | Event-loop lag < 50 ms while 10 streams run. | R1, R6 | [12 empty] | Sub
A1.3 | Retry policy with backoff + jitter | Ahmed Hamdy | 6 | 0.75 |  |  | 2 | 3 | 2026-10-01 | 2026-10-02 | 429 bursts recover without retry storms. | R4, R5 | [12 empty] | Sub
A1.4 | Per-model concurrency limits | Ahmed Hamdy | 6 | 0.75 |  |  | 3 | 4 | 2026-10-02 | 2026-10-03 | Limits configurable per model and per environment. | R6 | [12 empty] | Sub
A1.5 | Concurrency tests | Ahmed Hamdy | 6 | 0.75 |  |  | 4 | 4 | 2026-10-03 | 2026-10-03 | Test green in CI. | R1 | [12 empty] | Sub
A2 | Azure foundation: VNet, private DNS + endpoints, Key Vault, managed identities, App Insights | Ahmed Hamdy | 32 | 4 | — (day 1) | A1 | 5 | 8 | 2026-10-04 | 2026-10-09 |  |  | W1: 8; W2: 24 | Task
A2.1 | VNet, subnets and NSGs (IaC) | Ahmed Hamdy | 8 | 1 |  |  | 5 | 5 | 2026-10-04 | 2026-10-04 | Deployed from code; re-runnable. | R7 | [12 empty] | Sub
A2.2 | Private endpoints + private DNS | Ahmed Hamdy | 8 | 1 |  |  | 6 | 6 | 2026-10-07 | 2026-10-07 | nslookup from app subnet resolves to 10.20.x.x. | R7 | [12 empty] | Sub
A2.3 | Key Vault, managed identities, RBAC | Ahmed Hamdy | 8 | 1 |  |  | 7 | 7 | 2026-10-08 | 2026-10-08 | No secrets in code, env files or pipelines. | R8, R9 | [12 empty] | Sub
A2.4 | App Insights via OpenTelemetry | Ahmed Hamdy | 8 | 1 |  |  | 8 | 8 | 2026-10-09 | 2026-10-09 | Traces visible; PHI scan of logs is clean. | R10 | [12 empty] | Sub
A3 | CI/CD pipeline and staging environment | Ahmed Hamdy | 24 | 3 | A2 | A2 | 9 | 11 | 2026-10-10 | 2026-10-14 |  |  | W2: 16; W3: 8 | Task | A2
A3.1 | CI pipeline | Ahmed Hamdy | 10 | 1.25 |  |  | 9 | 10 | 2026-10-10 | 2026-10-11 | Pipeline green on main. | R11 | [12 empty] | Sub
A3.2 | Staging environment | Ahmed Hamdy | 8 | 1 |  |  | 10 | 11 | 2026-10-11 | 2026-10-14 | Staging reachable only on private network. | R8, R11 | [12 empty] | Sub
A3.3 | Release gates | Ahmed Hamdy | 6 | 0.75 |  |  | 11 | 11 | 2026-10-14 | 2026-10-14 | Failed smoke test blocks release. | R11 | [12 empty] | Sub
A6 | Diarization + Doctor/Patient role service (Arabic and English) | Ahmed Hamdy | 64 | 8 | A2, X6 | A3 | 12 | 19 | 2026-10-15 | 2026-10-24 |  |  | W3: 32; W4: 32 | Task | A2 | X6
A6.1 | Select diarization approach | Ahmed Hamdy | 8 | 1 |  |  | 12 | 12 | 2026-10-15 | 2026-10-15 | Approach chosen with sample DER. | R17 | [12 empty] | Sub
A6.2 | Streaming segmentation design | Ahmed Hamdy | 12 | 1.5 |  |  | 13 | 14 | 2026-10-16 | 2026-10-17 | Labels stable across a 10-minute session. | R17 | [12 empty] | Sub
A6.3 | Doctor / Patient role classification | Ahmed Hamdy | 12 | 1.5 |  |  | 14 | 15 | 2026-10-17 | 2026-10-18 | Role accuracy measurable on test set. | R17, R32 | [12 empty] | Sub
A6.4 | Diarization service + API | Ahmed Hamdy | 12 | 1.5 |  |  | 16 | 17 | 2026-10-21 | 2026-10-22 | Service live in staging behind private endpoint. | R14 | [12 empty] | Sub
A6.5 | Align words to speakers | Ahmed Hamdy | 12 | 1.5 |  |  | 17 | 18 | 2026-10-22 | 2026-10-23 | Transcript shows Doctor:/Patient: per turn. | R17 | [12 empty] | Sub
A6.6 | DER test harness | Ahmed Hamdy | 8 | 1 |  |  | 19 | 19 | 2026-10-24 | 2026-10-24 | DER and role accuracy reported per language. | R17 | [12 empty] | Sub
A4 | Deploy Foundry models: GPT-4o mini, GPT-5.6 Luna / Terra / Sol, structuring LLM | Ahmed Hamdy | 16 | 2 | A2 | A6 | 20 | 21 | 2026-10-25 | 2026-10-28 |  |  | W4: 8; W5: 8 | Task | A2
A4.1 | Deploy Foundry models | Ahmed Hamdy | 8 | 1 |  |  | 20 | 20 | 2026-10-25 | 2026-10-25 | All endpoints reachable via private endpoint. | R12 | [12 empty] | Sub
A4.2 | Structured-output smoke tests | Ahmed Hamdy | 4 | 0.5 |  |  | 21 | 21 | 2026-10-28 | 2026-10-28 | Valid JSON from every model. | R13 | [12 empty] | Sub
A4.3 | Content filter + config registration | Ahmed Hamdy | 4 | 0.5 |  |  | 21 | 21 | 2026-10-28 | 2026-10-28 | No false blocks on 20 clinical samples. | R12 | [12 empty] | Sub
A8 | Munsit private deployment in VNet (with vendor) | Ahmed Hamdy | 40 | 5 | X5, A3 | A4 | 22 | 26 | 2026-10-29 | 2026-11-04 |  |  | W5: 32; W6: 8 | Task | X5 | A3
A8.1 | Review vendor package | Ahmed Hamdy | 6 | 0.75 |  |  | 22 | 22 | 2026-10-29 | 2026-10-29 | Requirements signed off. | R33 | [12 empty] | Sub
A8.2 | Provision GPU node pool in VNet | Ahmed Hamdy | 12 | 1.5 |  |  | 22 | 24 | 2026-10-29 | 2026-10-31 | Nodes ready, no public IP. | R7, R33 | [12 empty] | Sub
A8.3 | Deploy Munsit containers | Ahmed Hamdy | 12 | 1.5 |  |  | 24 | 25 | 2026-10-31 | 2026-11-01 | Arabic streaming works inside VNet. | R8, R33 | [12 empty] | Sub
A8.4 | Wire into provider adapter | Ahmed Hamdy | 6 | 0.75 |  |  | 25 | 26 | 2026-11-01 | 2026-11-04 | Dropdown “Arabic” uses private Munsit. | R33 | [12 empty] | Sub
A8.5 | Monitoring | Ahmed Hamdy | 4 | 0.5 |  |  | 26 | 26 | 2026-11-04 | 2026-11-04 | Dashboards and alerts live. | R10 | [12 empty] | Sub
A5 | Deploy Voxtral Realtime on A10 endpoint (480 ms delay) | Ahmed Hamdy | 24 | 3 | A3, X6 | A8 | 27 | 29 | 2026-11-05 | 2026-11-07 |  |  | W6: 24 | Task | A3 | X6
A5.1 | Serve Voxtral on A10 endpoint | Ahmed Hamdy | 12 | 1.5 |  |  | 27 | 28 | 2026-11-05 | 2026-11-06 | Endpoint live in staging. | R14, R15, R16 | [12 empty] | Sub
A5.2 | 480 ms delay + WebSocket bridge | Ahmed Hamdy | 8 | 1 |  |  | 28 | 29 | 2026-11-06 | 2026-11-07 | Live English transcript in the app. | R15 | [12 empty] | Sub
A5.3 | Latency measurement | Ahmed Hamdy | 4 | 0.5 |  |  | 29 | 29 | 2026-11-07 | 2026-11-07 | Numbers recorded in the test log. | R15, R32 | [12 empty] | Sub
A11 | Load-test harness (WebSocket + SSE sessions) | Ahmed Hamdy | 16 | 2 | A3 | A5 | 30 | 31 | 2026-11-08 | 2026-11-11 |  |  | W6: 8; W7: 8 | Task | A3
A11.1 | Session replay script | Ahmed Hamdy | 10 | 1.25 |  |  | 30 | 31 | 2026-11-08 | 2026-11-11 | One script covers both languages and modes. | R22 | [12 empty] | Sub
A11.2 | Metrics export | Ahmed Hamdy | 6 | 0.75 |  |  | 31 | 31 | 2026-11-11 | 2026-11-11 | Per-session timings exported. | R10, R22 | [12 empty] | Sub
A13 | Load test 1→100 sessions per language on private stack; failover test | Ahmed Hamdy | 40 | 5 | A11, A12, A8, A5, A6, X7 | A11 | 32 | 36 | 2026-11-12 | 2026-11-18 |  |  | W7: 32; W8: 8 | Task | A11 | A12 | A8 | A5 | A6 | X7
A13.1 | Ramp test per language | Ahmed Hamdy | 16 | 2 |  |  | 32 | 33 | 2026-11-12 | 2026-11-13 | p50/p95/p99, 429 rate and failures per step. | R22, R32 | [12 empty] | Sub
A13.2 | Accuracy under load | Ahmed Hamdy | 8 | 1 |  |  | 34 | 34 | 2026-11-14 | 2026-11-14 | Accuracy delta recorded. | R21, R32 | [12 empty] | Sub
A13.3 | Failover under load | Ahmed Hamdy | 8 | 1 |  |  | 35 | 35 | 2026-11-15 | 2026-11-15 | Recovery time recorded. | R32 | [12 empty] | Sub
A13.4 | Tune limits and report | Ahmed Hamdy | 8 | 1 |  |  | 36 | 36 | 2026-11-18 | 2026-11-18 | Signed capacity report. | R32 | [12 empty] | Sub
A10 | Google STT ar-SA fallback benchmark on same audio set | Ahmed Hamdy | 16 | 2 | C2, M2 | A13 | 37 | 38 | 2026-11-19 | 2026-11-20 |  |  | W8: 16 | Task | C2 | M2
A10.1 | Google STT V2 adapter | Ahmed Hamdy | 8 | 1 |  |  | 37 | 37 | 2026-11-19 | 2026-11-19 | Adapter switch works in staging. | R20 | [12 empty] | Sub
A10.2 | Fallback benchmark | Ahmed Hamdy | 8 | 1 |  |  | 38 | 38 | 2026-11-20 | 2026-11-20 | Fallback decision documented. | R20, R21 | [12 empty] | Sub
A15 | Munsit private parity check: same audio set, compare with API results | Ahmed Hamdy | 8 | 1 | A8, A9 | A10 | 39 | 39 | 2026-11-21 | 2026-11-21 |  |  | W8: 8 | Task | A8 | A9
A15.1 | Munsit private parity check | Ahmed Hamdy | 8 | 1 |  |  | 39 | 39 | 2026-11-21 | 2026-11-21 | Parity confirmed or issue raised with vendor. | R21, R33 | [12 empty] | Sub
A14 | Final GPU sizing, replica plan and cost update | Ahmed Hamdy | 8 | 1 | A13 | A15 | 40 | 40 | 2026-11-22 | 2026-11-22 |  |  | W8: 8 | Task | A13
A14.1 | GPU sizing and cost | Ahmed Hamdy | 8 | 1 |  |  | 40 | 40 | 2026-11-22 | 2026-11-22 | Capacity and budget approved. | R32 | [12 empty] | Sub
DOHA — Clinical AI & evaluation
B2 | Structuring prompt + schema: sections, translation, speaker labels, no-inference rules, routing signals | Doha | 32 | 4 | — (day 1) | — | 1 | 4 | 2026-09-30 | 2026-10-03 |  |  | W1: 32 | Task
B2.1 | Structured note schema | Doha | 8 | 1 |  |  | 1 | 1 | 2026-09-30 | 2026-09-30 | Schema reviewed by Clinical Lead. | R13, R32 | [12 empty] | Sub
B2.2 | Prompt with fidelity rules | Doha | 8 | 1 |  |  | 2 | 2 | 2026-10-01 | 2026-10-01 | Rules embedded in prompt. | R32 | [12 empty] | Sub
B2.3 | Bilingual few-shot examples | Doha | 8 | 1 |  |  | 3 | 3 | 2026-10-02 | 2026-10-02 | 6–8 examples approved. | R32 | [12 empty] | Sub
B2.4 | Fidelity unit tests | Doha | 8 | 1 |  |  | 4 | 4 | 2026-10-03 | 2026-10-03 | All 20 tests pass. | R32 | [12 empty] | Sub
B4 | Reasoning prompt: ICD-10 (edition stated), diagnosis, rationale, ER triage, gaps, plan review, citations | Doha | 32 | 4 | B2 | B2 | 5 | 8 | 2026-10-04 | 2026-10-09 |  |  | W1: 8; W2: 24 | Task | B2
B4.1 | Reasoning output schema | Doha | 8 | 1 |  |  | 5 | 5 | 2026-10-04 | 2026-10-04 | Schema validates with strict mode. | R13 | [12 empty] | Sub
B4.2 | ICD-10 edition rules | Doha | 8 | 1 |  |  | 6 | 6 | 2026-10-07 | 2026-10-07 | No mixed-edition codes in tests. | R30 | [12 empty] | Sub
B4.3 | History scope + citation rules | Doha | 8 | 1 |  |  | 7 | 7 | 2026-10-08 | 2026-10-08 | Rules enforced in prompt and schema. | R32 | [12 empty] | Sub
B4.4 | Reasoning tests | Doha | 8 | 1 |  |  | 8 | 8 | 2026-10-09 | 2026-10-09 | All 15 cases reviewed by clinician. | R32 | [12 empty] | Sub
B3 | Incremental structuring: per-segment during dictation + final consolidation | Doha | 24 | 3 | B2 | B4 | 9 | 11 | 2026-10-10 | 2026-10-14 |  |  | W2: 16; W3: 8 | Task | B2
B3.1 | Segment trigger + running context | Doha | 8 | 1 |  |  | 9 | 9 | 2026-10-10 | 2026-10-10 | Note builds while doctor speaks. | R32 | [12 empty] | Sub
B3.2 | Consolidation pass | Doha | 8 | 1 |  |  | 10 | 10 | 2026-10-11 | 2026-10-11 | Final note in ≤ 3 s after stop. | R32 | [12 empty] | Sub
B3.3 | Incremental vs one-shot check | Doha | 8 | 1 |  |  | 11 | 11 | 2026-10-14 | 2026-10-14 | No fidelity loss vs one-shot. | R32 | [12 empty] | Sub
B5 | Extraction prompts per specialty (ER / OPD / Dental): note fields only | Doha | 24 | 3 | B2 | B3 | 12 | 14 | 2026-10-15 | 2026-10-17 |  |  | W3: 24 | Task | B2
B5.1 | Split extraction schemas | Doha | 12 | 1.5 |  |  | 12 | 13 | 2026-10-15 | 2026-10-16 | Three schemas committed. | R13, R25 | [12 empty] | Sub
B5.2 | Extraction prompt rules | Doha | 6 | 0.75 |  |  | 13 | 14 | 2026-10-16 | 2026-10-17 | Prompt approved. | R32 | [12 empty] | Sub
B5.3 | Schema validity tests | Doha | 6 | 0.75 |  |  | 14 | 14 | 2026-10-17 | 2026-10-17 | All outputs valid. | R25 | [12 empty] | Sub
B6 | Reasoning router: rule-based tiers (MedGemma 27B → Terra → Sol), escalation, audit | Doha | 16 | 2 | B4 | B5 | 15 | 16 | 2026-10-18 | 2026-10-21 |  |  | W3: 8; W4: 8 | Task | B4
B6.1 | Routing rules | Doha | 8 | 1 |  |  | 15 | 15 | 2026-10-18 | 2026-10-18 | Unit tests per trigger. | R32 | [12 empty] | Sub
B6.2 | Escalation + audit | Doha | 8 | 1 |  |  | 16 | 16 | 2026-10-21 | 2026-10-21 | Audit entry for every routed case. | R32 | [12 empty] | Sub
B1 | Port term correction; clinical review of red-flag lexicon | Doha | 16 | 2 | — (day 1) | B6 | 17 | 18 | 2026-10-22 | 2026-10-23 |  |  | W4: 16 | Task
B1.1 | Port term correction | Doha | 8 | 1 |  |  | 17 | 17 | 2026-10-22 | 2026-10-22 | Corrections logged per session. | R32 | [12 empty] | Sub
B1.2 | Lexicon review + tests | Doha | 8 | 1 |  |  | 18 | 18 | 2026-10-23 | 2026-10-23 | Lexicon signed off; tests pass. | R32 | [12 empty] | Sub
A7 | Deploy MedGemma 27B (A100/H100) and MedGemma 4B endpoints | Doha | 32 | 4 | A3, X6 | B1 | 19 | 22 | 2026-10-24 | 2026-10-29 |  |  | W4: 16; W5: 16 | Task | A3 | X6
A7.1 | Model access | Doha | 4 | 0.5 |  |  | 19 | 19 | 2026-10-24 | 2026-10-24 | Weights in private storage. | R18, R19 | [12 empty] | Sub
A7.2 | MedGemma 27B on A100 80GB | Doha | 12 | 1.5 |  |  | 19 | 20 | 2026-10-24 | 2026-10-25 | Endpoint live via private endpoint. | R14, R16, R18 | [12 empty] | Sub
A7.3 | MedGemma 4B on A10 | Doha | 8 | 1 |  |  | 21 | 21 | 2026-10-28 | 2026-10-28 | Endpoint live. | R16, R19 | [12 empty] | Sub
A7.4 | Structured-output smoke test | Doha | 8 | 1 |  |  | 22 | 22 | 2026-10-29 | 2026-10-29 | Valid JSON; p50 latency recorded. | R16 | [12 empty] | Sub
B8 | Benchmark structuring fidelity and extraction (4o mini vs Luna vs MedGemma 4B) | Doha | 24 | 3 | C3, M5, A4, A7 | A7 | 23 | 25 | 2026-10-30 | 2026-11-01 |  |  | W5: 24 | Task | C3 | M5 | A4 | A7
B8.1 | Structuring fidelity | Doha | 8 | 1 |  |  | 23 | 23 | 2026-10-30 | 2026-10-30 | Fidelity score per language. | R32 | [12 empty] | Sub
B8.2 | Extraction comparison | Doha | 12 | 1.5 |  |  | 24 | 25 | 2026-10-31 | 2026-11-01 | Ranked results table. | R19, R31 | [12 empty] | Sub
B8.3 | Decision memo | Doha | 4 | 0.5 |  |  | 25 | 25 | 2026-11-01 | 2026-11-01 | Memo approved by Architect. | R32 | [12 empty] | Sub
A12 | Resilience: health checks, circuit breakers, model + speech fallback, admission control | Doha | 24 | 3 | M5 | B8 | 26 | 28 | 2026-11-04 | 2026-11-06 |  |  | W6: 24 | Task | M5
A12.1 | Health and readiness probes | Doha | 6 | 0.75 |  |  | 26 | 26 | 2026-11-04 | 2026-11-04 | Probes used by gateway and deploy. | R14 | [12 empty] | Sub
A12.2 | Circuit breakers | Doha | 8 | 1 |  |  | 26 | 27 | 2026-11-04 | 2026-11-05 | Failing provider isolated automatically. | R23 | [12 empty] | Sub
A12.3 | Fallback chains | Doha | 6 | 0.75 |  |  | 27 | 28 | 2026-11-05 | 2026-11-06 | Fallback exercised in tests. | R4, R32 | [12 empty] | Sub
A12.4 | Admission control | Doha | 4 | 0.5 |  |  | 28 | 28 | 2026-11-06 | 2026-11-06 | Overload test shows clean rejects. | R6 | [12 empty] | Sub
B9 | Reasoning benchmark: default-model gate (27B vs Terra), router calibration | Doha | 24 | 3 | C3, M5, A7 | A12 | 29 | 31 | 2026-11-07 | 2026-11-11 |  |  | W6: 16; W7: 8 | Task | C3 | M5 | A7
B9.1 | 27B vs Terra run | Doha | 12 | 1.5 |  |  | 29 | 30 | 2026-11-07 | 2026-11-08 | Results table complete. | R18, R31 | [12 empty] | Sub
B9.2 | Default-model gate | Doha | 4 | 0.5 |  |  | 30 | 30 | 2026-11-08 | 2026-11-08 | Gate decision recorded. | R32 | [12 empty] | Sub
B9.3 | Router calibration | Doha | 8 | 1 |  |  | 31 | 31 | 2026-11-11 | 2026-11-11 | Triggers updated. | R32 | [12 empty] | Sub
B10 | Run current product on gold set (As-Is baseline) | Doha | 8 | 1 | C3 | B9 | 32 | 32 | 2026-11-12 | 2026-11-12 |  |  | W7: 8 | Task | C3
B10.1 | As-Is baseline run | Doha | 8 | 1 |  |  | 32 | 32 | 2026-11-12 | 2026-11-12 | Baseline file delivered to reviewers. | R32 | [12 empty] | Sub
B11 | End-to-end run of new pipeline on gold set | Doha | 8 | 1 | B8, B9 | B10 | 33 | 33 | 2026-11-13 | 2026-11-13 |  |  | W7: 8 | Task | B8 | B9
B11.1 | End-to-end run | Doha | 8 | 1 |  |  | 33 | 33 | 2026-11-13 | 2026-11-13 | File delivered to reviewers. | R32 | [12 empty] | Sub
A9 | Speech benchmark: WER/CER, medical terms, role accuracy (Munsit, Voxtral, diarization) | Doha | 24 | 3 | A5, A6, C2, M2 | B11 | 34 | 36 | 2026-11-14 | 2026-11-18 |  |  | W7: 16; W8: 8 | Task | A5 | A6 | C2 | M2
A9.1 | Run speech set | Doha | 8 | 1 |  |  | 34 | 34 | 2026-11-14 | 2026-11-14 | All files processed. | R17, R21 | [12 empty] | Sub
A9.2 | WER / CER with Arabic normalization | Doha | 8 | 1 |  |  | 35 | 35 | 2026-11-15 | 2026-11-15 | WER/CER per engine and mode. | R21 | [12 empty] | Sub
A9.3 | DER, roles, medical terms | Doha | 8 | 1 |  |  | 36 | 36 | 2026-11-18 | 2026-11-18 | Speech report signed. | R17, R21 | [12 empty] | Sub
B12 | Fix gaps found by clinicians; re-run failed cases | Doha | 24 | 3 | C5 | A9 | 37 | 39 | 2026-11-19 | 2026-11-21 |  |  | W8: 24 | Task | C5
B12.1 | Fix and re-run | Doha | 24 | 3 |  |  | 37 | 39 | 2026-11-19 | 2026-11-21 | Gate metrics met. | R32 | [12 empty] | Sub
MOHAMED ESSAM — Integration & application
M1 | Clinical AI Gateway (API Management): Entra auth, rate limits, audit, admission control | Mohamed Essam | 24 | 3 | — (day 1) | — | 1 | 3 | 2026-09-30 | 2026-10-02 |  |  | W1: 24 | Task
M1.1 | API Management instance | Mohamed Essam | 8 | 1 |  |  | 1 | 1 | 2026-09-30 | 2026-09-30 | Gateway reachable privately. | R26 | [12 empty] | Sub
M1.2 | Policies | Mohamed Essam | 8 | 1 |  |  | 2 | 2 | 2026-10-01 | 2026-10-01 | Policies tested. | R26, R9 | [12 empty] | Sub
M1.3 | Backends | Mohamed Essam | 8 | 1 |  |  | 3 | 3 | 2026-10-02 | 2026-10-02 | All model calls go through gateway. | R26 | [12 empty] | Sub
M8 | Security: threat model, dashboard behind Entra ID, PHI-safe logging | Mohamed Essam | 24 | 3 | M1 | M1 | 4 | 6 | 2026-10-03 | 2026-10-07 |  |  | W1: 16; W2: 8 | Task | M1
M8.1 | Threat model | Mohamed Essam | 8 | 1 |  |  | 4 | 4 | 2026-10-03 | 2026-10-03 | Threat model approved by Security. | R27 | [12 empty] | Sub
M8.2 | Dashboard behind Entra ID | Mohamed Essam | 8 | 1 |  |  | 5 | 5 | 2026-10-04 | 2026-10-04 | Unauthenticated access returns 401. | R9 | [12 empty] | Sub
M8.3 | PHI-safe logging | Mohamed Essam | 8 | 1 |  |  | 6 | 6 | 2026-10-07 | 2026-10-07 | PHI scan of logs is clean. | R10, R27 | [12 empty] | Sub
M4 | Validation layer: ICD-10 check, schema, diagnosis–findings consistency, history cross-check, checklist | Mohamed Essam | 32 | 4 | B2, X3 | M8 | 7 | 10 | 2026-10-08 | 2026-10-11 |  |  | W2: 32 | Task | B2 | X3
M4.1 | ICD-10 code table | Mohamed Essam | 6 | 0.75 |  |  | 7 | 7 | 2026-10-08 | 2026-10-08 | Lookup < 1 ms. | R30 | [12 empty] | Sub
M4.2 | Schema validation | Mohamed Essam | 6 | 0.75 |  |  | 7 | 8 | 2026-10-08 | 2026-10-09 | Invalid output rejected with reason. | R25 | [12 empty] | Sub
M4.3 | Diagnosis–findings consistency | Mohamed Essam | 8 | 1 |  |  | 8 | 9 | 2026-10-09 | 2026-10-10 | Cautions shown to doctor. | R32 | [12 empty] | Sub
M4.4 | History cross-check + checklist | Mohamed Essam | 8 | 1 |  |  | 9 | 10 | 2026-10-10 | 2026-10-11 | Existing behaviour preserved. | R32 | [12 empty] | Sub
M4.5 | Validation tests | Mohamed Essam | 4 | 0.5 |  |  | 10 | 10 | 2026-10-11 | 2026-10-11 | All rules covered. | R25 | [12 empty] | Sub
M2 | Provider adapter + language-dropdown wiring (OpenRouter → Foundry / private STT) | Mohamed Essam | 16 | 2 | M1, A1 | M4 | 11 | 12 | 2026-10-14 | 2026-10-15 |  |  | W3: 16 | Task | M1 | A1
M2.1 | Provider interfaces | Mohamed Essam | 8 | 1 |  |  | 11 | 11 | 2026-10-14 | 2026-10-14 | Switch provider without code change. | R1 | [12 empty] | Sub
M2.2 | Dropdown → engine mapping | Mohamed Essam | 8 | 1 |  |  | 12 | 12 | 2026-10-15 | 2026-10-15 | Mapping covered by tests. | R32 | [12 empty] | Sub
M3 | Build clinical gold set: sample 100 logged sessions (70% Arabic/mixed), de-identify | Mohamed Essam | 8 | 1 | X1 | M2 | 13 | 13 | 2026-10-16 | 2026-10-16 |  |  | W3: 8 | Task | X1
M3.1 | Build clinical gold set | Mohamed Essam | 8 | 1 |  |  | 13 | 13 | 2026-10-16 | 2026-10-16 | De-identified package delivered. | R24 | [12 empty] | Sub
M7 | Patient-history service: SQL source, 12-month scope, influence rules | Mohamed Essam | 24 | 3 | A2 | M3 | 14 | 16 | 2026-10-17 | 2026-10-21 |  |  | W3: 16; W4: 8 | Task | A2
M7.1 | History SQL views | Mohamed Essam | 12 | 1.5 |  |  | 14 | 15 | 2026-10-17 | 2026-10-18 | Read-only account; no dynamic SQL. | R32 | [12 empty] | Sub
M7.2 | Format for reasoning | Mohamed Essam | 6 | 0.75 |  |  | 15 | 16 | 2026-10-18 | 2026-10-21 | Same format as today. | R32 | [12 empty] | Sub
M7.3 | Tests | Mohamed Essam | 6 | 0.75 |  |  | 16 | 16 | 2026-10-21 | 2026-10-21 | Tests pass. | R32 | [12 empty] | Sub
B7 | Carry forward: patient-history rules, voice-fill via structuring, consent line | Mohamed Essam | 16 | 2 | B3, B4 | M7 | 17 | 18 | 2026-10-22 | 2026-10-23 |  |  | W4: 16 | Task | B3 | B4
B7.1 | Voice-fill via structuring | Mohamed Essam | 8 | 1 |  |  | 17 | 17 | 2026-10-22 | 2026-10-22 | Voice-fill works in both languages. | R32 | [12 empty] | Sub
B7.2 | Consent line + history rules | Mohamed Essam | 8 | 1 |  |  | 18 | 18 | 2026-10-23 | 2026-10-23 | Rules verified in tests. | R32 | [12 empty] | Sub
M5 | Parallel orchestration (extraction ∥ tiered reasoning) + progressive SSE | Mohamed Essam | 24 | 3 | A1, M2, B1, B3, B5, B6, M4 | B7 | 19 | 21 | 2026-10-24 | 2026-10-28 |  |  | W4: 16; W5: 8 | Task | A1 | M2 | B1 | B3 | B5 | B6 | M4
M5.1 | Parallel execution | Mohamed Essam | 12 | 1.5 |  |  | 19 | 20 | 2026-10-24 | 2026-10-25 | Stage time ≈ slower branch. | R6 | [12 empty] | Sub
M5.2 | Merge, validate, escalate | Mohamed Essam | 8 | 1 |  |  | 20 | 21 | 2026-10-25 | 2026-10-28 | Merged output passes schema. | R25, R32 | [12 empty] | Sub
M5.3 | SSE event contract | Mohamed Essam | 4 | 0.5 |  |  | 21 | 21 | 2026-10-28 | 2026-10-28 | UI consumes all events. | R28 | [12 empty] | Sub
M10 | HIS/EMR write-back after physician approval (with HIS team) | Mohamed Essam | 48 | 6 | X8, M5 | M5 | 22 | 27 | 2026-10-29 | 2026-11-05 |  |  | W5: 32; W6: 16 | Task | X8 | M5
M10.1 | Map note to HIS format | Mohamed Essam | 12 | 1.5 |  |  | 22 | 23 | 2026-10-29 | 2026-10-30 | Mapping signed by HIS team. | R29 | [12 empty] | Sub
M10.2 | Approval-gated commit | Mohamed Essam | 12 | 1.5 |  |  | 23 | 24 | 2026-10-30 | 2026-10-31 | No duplicate notes on retry. | R29 | [12 empty] | Sub
M10.3 | Retry queue and errors | Mohamed Essam | 8 | 1 |  |  | 25 | 25 | 2026-11-01 | 2026-11-01 | No silent failures. | R4 | [12 empty] | Sub
M10.4 | Integration test with HIS | Mohamed Essam | 12 | 1.5 |  |  | 26 | 27 | 2026-11-04 | 2026-11-05 | HIS team sign-off. | R29 | [12 empty] | Sub
M10.5 | Audit | Mohamed Essam | 4 | 0.5 |  |  | 27 | 27 | 2026-11-05 | 2026-11-05 | Audit visible in dashboard. | R32 | [12 empty] | Sub
M6 | UI: progressive results, citations, cautions, re-run reasoning, speaker confirmation | Mohamed Essam | 40 | 5 | M5 | M10 | 28 | 32 | 2026-11-06 | 2026-11-12 |  |  | W6: 24; W7: 16 | Task | M5
M6.1 | Progressive rendering | Mohamed Essam | 8 | 1 |  |  | 28 | 28 | 2026-11-06 | 2026-11-06 | No blank screen while waiting. | R28 | [12 empty] | Sub
M6.2 | Citation click-through | Mohamed Essam | 8 | 1 |  |  | 29 | 29 | 2026-11-07 | 2026-11-07 | Works for all outputs. | R32 | [12 empty] | Sub
M6.3 | Caution banners | Mohamed Essam | 8 | 1 |  |  | 30 | 30 | 2026-11-08 | 2026-11-08 | Cautions visible and dismissible with reason. | R32 | [12 empty] | Sub
M6.4 | Re-run reasoning + speaker confirm | Mohamed Essam | 12 | 1.5 |  |  | 31 | 32 | 2026-11-11 | 2026-11-12 | Both flows usable. | R32 | [12 empty] | Sub
M6.5 | RTL and accessibility check | Mohamed Essam | 4 | 0.5 |  |  | 32 | 32 | 2026-11-12 | 2026-11-12 | Checklist passed. | R32 | [12 empty] | Sub
M9 | Migrate usage/feedback analytics to secure telemetry | Mohamed Essam | 16 | 2 | A3 | M6 | 33 | 34 | 2026-11-13 | 2026-11-14 |  |  | W7: 16 | Task | A3
M9.1 | Telemetry events | Mohamed Essam | 8 | 1 |  |  | 33 | 33 | 2026-11-13 | 2026-11-13 | Events visible. | R10 | [12 empty] | Sub
M9.2 | Dashboard workbook | Mohamed Essam | 8 | 1 |  |  | 34 | 34 | 2026-11-14 | 2026-11-14 | Workbook shared with admins. | R10 | [12 empty] | Sub
M11 | Functional regression test against current product | Mohamed Essam | 24 | 3 | M6, B7, M7, M10, M9 | M9 | 35 | 37 | 2026-11-15 | 2026-11-19 |  |  | W7: 8; W8: 16 | Task | M6 | B7 | M7 | M10 | M9
M11.1 | Regression matrix | Mohamed Essam | 16 | 2 |  |  | 35 | 36 | 2026-11-15 | 2026-11-18 | All scenarios executed. | R32 | [12 empty] | Sub
M11.2 | Defect triage | Mohamed Essam | 8 | 1 |  |  | 37 | 37 | 2026-11-19 | 2026-11-19 | No open S1/S2. | R32 | [12 empty] | Sub
M12 | Fix penetration-test findings | Mohamed Essam | 16 | 2 | C6 | M11 | 38 | 39 | 2026-11-20 | 2026-11-21 |  |  | W8: 16 | Task | C6
M12.1 | Fix pen-test findings | Mohamed Essam | 16 | 2 |  |  | 38 | 39 | 2026-11-20 | 2026-11-21 | Security sign-off. | R27 | [12 empty] | Sub
CLINICAL, SECURITY & USER ACCEPTANCE (outside the AI team)
C1 | Record speech test set: ~40 encounters (70% Arabic/mixed, both modes) | Clinical team | 20 | 5 | X2 | — | 11 | 15 | 2026-10-14 | 2026-10-18 | [14 empty] | Task | X2 | bar: W3
C1.1 | Record speech test set | Clinical team | 20 |  |  |  | 11 | 15 | 2026-10-14 | 2026-10-18 | Audio set complete. | R32 | [12 empty] | Sub
C2 | Annotate speech test set: reference transcripts, speaker roles | Clinical reviewers | 24 | 4 | C1 | — | 16 | 19 | 2026-10-21 | 2026-10-24 | [14 empty] | Task | C1 | bar: W4
C2.1 | Reference transcripts + roles | Clinical reviewers | 24 |  |  |  | 16 | 19 | 2026-10-21 | 2026-10-24 | References complete. | R17, R21 | [12 empty] | Sub
C3 | Annotate 100-encounter clinical gold set (fields, ICD-10, diagnosis) | Clinical reviewers | 60 | 6 | M3 | — | 14 | 19 | 2026-10-17 | 2026-10-24 | [14 empty] | Task | M3 | bar: W3 to W4
C3.1 | Annotate gold set | Clinical reviewers | 60 |  |  |  | 14 | 19 | 2026-10-17 | 2026-10-24 | Gold set frozen. | R32 | [12 empty] | Sub
C4 | Score As-Is baseline outputs | Clinical reviewers | 17 | 2 | B10, C3 | — | 33 | 34 | 2026-11-13 | 2026-11-14 | [14 empty] | Task | B10 | C3 | bar: W7
C4.1 | Score As-Is outputs | Clinical reviewers | 17 |  |  |  | 33 | 34 | 2026-11-13 | 2026-11-14 | Baseline scores. | R32 | [12 empty] | Sub
C5 | Score new-pipeline outputs | Clinical reviewers | 17 | 2 | B11, C4 | — | 35 | 36 | 2026-11-15 | 2026-11-18 | [14 empty] | Task | B11 | C4 | bar: W7 to W8
C5.1 | Score new outputs | Clinical reviewers | 17 |  |  |  | 35 | 36 | 2026-11-15 | 2026-11-18 | New scores. | R32 | [12 empty] | Sub
C6 | Penetration test on staging | Security team | 24 | 3 | M8, A12, M5 | — | 29 | 31 | 2026-11-07 | 2026-11-11 | [14 empty] | Task | M8 | A12 | M5 | bar: W6 to W7
C6.1 | Penetration test | Security team | 24 |  |  |  | 29 | 31 | 2026-11-07 | 2026-11-11 | Findings report. | R27 | [12 empty] | Sub
C7 | Doctor training and quick guide | Product Owner | 12 | 2 | M6 | — | 33 | 34 | 2026-11-13 | 2026-11-14 | [14 empty] | Task | M6 | bar: W7
C7.1 | Training | Product Owner | 12 |  |  |  | 33 | 34 | 2026-11-13 | 2026-11-14 | Doctors trained. | R32 | [12 empty] | Sub
C8 | UAT with doctors (ER, OPD, Dental; Arabic and English; both modes) | Doctors + Clinical Lead | 24 | 3 | M11, A8 | — | 38 | 40 | 2026-11-20 | 2026-11-22 | [14 empty] | Task | M11 | A8 | bar: W8
C8.1 | UAT | Doctors + Clinical Lead | 24 |  |  |  | 38 | 40 | 2026-11-20 | 2026-11-22 | UAT sign-off. | R32 | [12 empty] | Sub
GATE, PILOT, GO-LIVE & HYPERCARE
G1 | Go-live gate: accuracy, load, security, UAT and residency criteria met | Steering + Clinical Lead | 4 | 1 | B12, A13, M12, X4, X7, C8, A14, A9, A10, A15 | — | 41 | 41 | 2026-11-25 | 2026-11-25 | [14 empty] | Task | B12 | A13 | M12 | X4 | X7 | C8 | A14 | A9 | A10 | A15 | bar: W9
G1.1 | Gate review | Steering + Clinical Lead | 4 |  |  |  | 41 | 41 | 2026-11-25 | 2026-11-25 | Go decision recorded. | R32 | [12 empty] | Sub
P1 | Controlled pilot at one site (rollback ready) | PM + Clinical Lead | 40 | 5 | G1, C7 | — | 42 | 46 | 2026-11-26 | 2026-12-02 | [14 empty] | Task | G1 | C7 | bar: W9 to W10
P1.1 | Controlled pilot | PM + Clinical Lead | 40 |  |  |  | 42 | 46 | 2026-11-26 | 2026-12-02 | Pilot stable. | R32 | [12 empty] | Sub
P2 | Go / no-go decision and production cutover | Steering | 8 | 1 | P1 | — | 47 | 47 | 2026-12-03 | 2026-12-03 | [14 empty] | Task | P1 | bar: W10
P2.1 | Production cutover | Steering | 8 |  |  |  | 47 | 47 | 2026-12-03 | 2026-12-03 | Production live. | R32 | [12 empty] | Sub
H1 | Hypercare: accuracy drift, latency, routing mix, adoption | AI team + Operations | 80 | 10 | P2 | — | 48 | 57 | 2026-12-04 | 2026-12-17 |  |  | W10: 3d; W11: 5d; W12: 2d | Task | P2
H1.1 | Hypercare | AI team + Operations | 80 |  |  |  | 48 | 57 | 2026-12-04 | 2026-12-17 | Stable operations. | R32 | [12 empty] | Sub